## Dashboard
DayOf Full V2 Milestone Tracker
Metric | Value | Notes
Macro milestones | 25 | Full-product areas required for honest V2.
Micro milestones | 123 | Executable slices with exit criteria.
P0 macro milestones | 7 | Release-critical or foundational.
P1 macro milestones | 14 | Core product quality.
P2 macro milestones | 4 | Important polish/proof depth.
Current local ahead count | Use git status | Ahead count changes with every local commit; final git status is the source of truth before push.
V2 release rule | All exit-bar gates green | No half-done V2: every P0/P1 consumer-facing gate must be proven, polished, truthful, or explicitly narrowed.
V2 closeout verdict | NOT SIGNOFF-READY | Exit Bar remains the release contract; use V2 Closeout Queue before marking V2 done.
V2 closeout queue | See V2 Closeout Queue | Splits test-only closures from actual work/narrowing and proof-infra drift.
Latest V2 queue audit | 2026-05-28 05:54 PM PT | Tracker refreshed after proof-board freshness returned to green; release-proof cleanup remains in progress.
Macro Status | Count | Formula
Not started
Scoping
In progress
Blocked
Needs proof
Done
Next Recommended Batches | Milestones | Purpose | Priority | Exit Signal
Batch 1 | V2-03, V2-04, V2-05, V2-22 | Make V2 real: schema, multi-page, runtime, migration, data integrity. | P0 | V2 doc renders publicly and can migrate from existing truth.
Batch 2 | V2-06, V2-07, V2-09 | Unify guest journey, RSVP, event RSVP, contact updates, guest ops. | P1 | Guest can move end-to-end without stale tokens or ops leaks.
Batch 3 | V2-08 | Owner registry, public registry, imports, cleanup, funds, thank-yous. | P1 | Registry public and dashboard truth stays synchronized.
Batch 4 | V2-10, V2-14 | Preview-safe messaging, texting readiness, delivery recovery, and coordinator command center. | P0 | Day-of operator can resolve issues and the SMS lane is ready for explicit enablement.
Batch 5 | V2-11, V2-12, V2-13 | Make planning data operational across vendors, timing, travel, seating. | P1 | Planning recommendations route to real actions and handoffs.

## V2 Closeout Queue
DayOf V2 Closeout Queue
Last refreshed | 2026-05-28 04:57 PM PT | Rule | Do not call V2 done until every Exit Bar gate is green or explicitly narrowed with honest product claims.
Rank | Bucket | Priority | Exit Gate(s) | Milestone(s) | Queue Item | Why it is here | What closes it | Verification / Evidence | Stop Condition
1 | Proof infra / release truth | P0 | V2-G14, V2-G07 | V2-25.01, V2-25.02, V2-25.05, V2-21.05 | Repair stale release-proof wiring | The proof surface is healthier now: ai-product-readiness is restored, and proof-board freshness is green again. The item still stays open until the remaining release-proof contract is reconciled. | Keep reconciling any stale proof aliases, keep BACKLOG current-state truth fresh, and record the exact release-proof contract the closeout relies on. | 2026-05-28 `proof:v1:ai-product-readiness` PASS 7/7, `proof:v1:board:freshness` PASS, and `proof:v1:board:md` PASS. | Do not use proof board or AI readiness as current launch truth until this is fixed.
2 | Test-first | P0 | V2-G03 | V2-03.06 | Builder V2 signed-in smoke | Automated builder gate is green, but exit bar still requires owner browser proof for builder, guide fallback, and legacy fallback feel. | Run signed-in desktop/mobile browser smoke for /dashboard/builder, /dashboard/builder-guide, and /dashboard/builder-v1 fallback paths. | Browser proof attached; no lab-only ambiguity; no dead builder handoff. | If smoke fails, patch the specific broken handoff instead of marking builder done.
3 | Test-first | P1 | V2-G02, V2-G01 | V2-01.05, V2-02, V2-03 | First-session couple path smoke | The first five minutes decide whether V2 feels real. Tracker says proof is still open. | Run signed-out and signed-in desktop/mobile first-session smoke from Home/Product/Signup/QuickStart through build/publish/share next step. | A new couple reaches a useful setup/build/publish state without internal language or fake readiness claims. | Any maze/dead-end/overclaim failure becomes a focused patch.
4 | Actual work | P0 | V2-G04 | V2-04, V2-05, V2-24.05 | Public V2 runtime and template parity | Exit Bar marks public V2 runtime parity Not started, so this cannot close by testing alone. | Build/prove V2 public renderer parity, template import/compatibility, visual proof, metadata, mobile, and leak boundaries. | Runtime tests, template matrix, visual proof set, mobile proof, and no private leaks. | Do not call Builder V2 complete if public V2 output is only schema-compatible or visually placeholder.
5 | Test-first | P1 | V2-G05 | V2-06, V2-07, V2-09, V2-15 | Zero-friction guest journey proof | Guest flows are strong in pieces, but tracker still lacks unified guest happy-path proof. | Run invite-linked mobile guest proof covering RSVP, schedule/travel, photo upload, contact update, registry, vault, and return-later behavior. | Guest happy path and stale/invalid link recovery pass without token/debug/provider/ops wording. | Patch failures in the specific guest surface before marking G05 done.
6 | Test-first | P1 | V2-G09 | V2-08.05 | Registry public parity proof | Registry dashboard work is advanced, but public purchased/hidden/fund/thank-you parity remains open. | Run public registry parity proof and focused registry suite. | Dashboard and public registry agree on purchased, partial, hidden, fund, cleanup, and thank-you-relevant state. | If parity fails, patch public/dashboard sync before closing registry trust.
7 | Narrow/provider-gated | P0 | V2-G06 | V2-10.04, V2-10.05, V2-10.06, V2-10.07, V2-10.08 | Messaging and SMS truth | SMS cannot be treated as live V2 unless sender/compliance/delivery proof exists. | Either fully prove provider/sender/consent/opt-out/live delivery/credit truth, or keep SMS disabled/narrowed with explicit product copy. | Provider readiness checklist and live-safe delivery readback, or disabled-state proof plus no public SMS overclaims. | Do not enable or market texting without compliance and delivery proof.
8 | Proof infra + narrowing | P0 | V2-G07, V2-G01 | V2-21.01 through V2-21.08 | AI product contract | The proof command is restored, and browser AI is now narrowed away from Vite-exposed keys. The gate is still open until claims and any retained server-backed lanes are fully reconciled. | Use restored ai-product-readiness proof, then finish claims-matrix review and any retained server-backed lane proof. | 2026-05-28 npm run proof:v1:ai-product-readiness passed 7/7 with deterministic fallback rails, assisted-copy assertions, public-boundary tests, and photo/vault safety checks. | Do not market AI beyond proven/narrowed lanes.
9 | Work + proof | P1 | V2-G08, V2-G05 | V2-15.05 through V2-15.08 | Photo, vault, and memory delight | Exit Bar marks this Not started; mobile upload/vault/recap polish needs proof. | Run mobile upload/vault proof, fix retry/progress/success/upload-more/moderation/recap rough edges, or narrow provider-dependent claims. | Mobile proof, vault contribution proof, moderation checks, recap/browser evidence. | Do not let brittle upload/vault flows block guests.
10 | Test/narrow | P1 | V2-G10 | V2-19.02, V2-19.03, V2-19.05 | Billing and entitlement trust | Billing is sensitive and must not overclaim provider readiness or fail open. | Run Stripe/session/bypass/entitlement safety tests and provider-backed proof if claims require it. | Local safety tests green plus provider-backed proof or narrowed billing claims. | Any fail-open or misleading billing state blocks V2.
11 | Proof-first | P0 | V2-G12 | V2-20.03, V2-22, V2-23 | Security, privacy, data integrity, safe errors | Many P0 data/security micro rows are Not started; this is release-blocking until proven. | Run token flow, service-role authorization, upload/URL safety, docs/log secret scan, adapter/hydration/import/export tests, and safe-error scans. | All relevant security/data/safe-error proofs green or explicitly deferred outside public claims. | Any guest/customer secret leak, token leak, or unsafe error blocks V2.
12 | Proof/narrowing | P1 | V2-G11 | V2-20.05 | Analytics and ops truth | Analytics/invite-funnel truth is Not started and must not be overclaimed. | Prove analytics shown to owners are accurate or narrow/remove unsupported analytics claims. | Analytics truth tests or copy narrowed to shipped behavior. | Do not claim analytics depth that is not implemented/proven.
13 | Release visual proof | P1 | V2-G13, V2-G04, V2-G05 | V2-24.01, V2-24.02, V2-24.04, V2-24.05 | Whole-product mobile, accessibility, and visual polish matrix | This is the final consumer-readiness pass and cannot happen meaningfully until core surfaces stabilize. | Run mobile route matrix, keyboard/form spot checks, visual overlap screenshots, and full polished-route pass. | No blocking mobile overlap, unreadable text, guest-facing rough edge, or a11y/form blocker remains. | Any major mobile/visual blocker keeps V2 open.
14 | Release docs / go-no-go | P0 | V2-G14 | V2-25.03, V2-25.04, V2-25.06 | Final V2 certification and rollback plan | Release signoff needs a human-readable proof packet and honest narrowed claims. | Reconcile tracker/proof docs, write release/rollback plan, run final QA cadence, and record exact remaining deferrals. | Exit Bar all green or narrowed; final proof bundle green; rollback plan recorded. | Do not call V2 complete from individual feature tests alone.

## Testing vs Build Split
Testing vs Build Split
Last refreshed | 2026-05-28 04:57 PM PT | Purpose | Use this to answer: what can be called done if tests pass vs what is not actually done/narrowed yet?
Bucket | Item | Related Gates | Why | Close Criteria | Next Proof/Work
Can close if testing passes | Builder V2 primary route/cutover | V2-G03 | Automated gate is already green; needs signed-in browser smoke. | Owner browser smoke green for builder, guide, and legacy fallback. | Run signed-in desktop/mobile builder smoke.
Can close if testing passes | First-session couple funnel | V2-G02, V2-G01 | Implementation may be close; proof is missing. | Signed-out/in desktop/mobile smoke reaches useful setup/build/publish path without overclaim. | Run first-session smoke and patch only failures.
Can close if testing passes | Registry public parity | V2-G09 | Likely proof-first lane after registry polish. | Public and dashboard registry state agree in focused suite/proof. | Run registry parity proof.
Can close if testing passes | Guest happy path | V2-G05 | Strong pieces exist; unified proof is missing. | Invite-linked mobile guest happy path and stale-link recovery pass. | Run mobile guest browser proof.
Can close if testing passes or narrowed | Billing entitlement trust | V2-G10 | Local safety may close, provider claims need proof/narrowing. | Entitlement/bypass tests green; provider-backed claims proven or narrowed. | Run Stripe/session/bypass tests and inspect copy.
Not done / needs actual work | Public V2 runtime parity and template visual matrix | V2-G04, V2-G13 | Tracker marks this Not started and it is foundational to V2. | V2 docs render polished public desktop/mobile sites with section parity. | Build/prove runtime, template matrix, visual set.
Not done / needs actual work | Release proof infrastructure | V2-G14 | The biggest freshness blocker is fixed: board freshness now passes, and ai-product-readiness is restored. Remaining work is narrower release-proof contract reconciliation. | Board freshness green, proof board render green, and any remaining relied-on proof aliases reconciled or honestly narrowed. | Continue release-proof cleanup from the closeout queue until no stale relied-on proof lane remains.
Not done / needs actual work or explicit narrowing | AI product contract | V2-G07, V2-G01 | AI readiness proof is restored and browser OpenAI key exposure is removed, but claims still need final cross-surface narrowing/readback. | Local AI readiness proof green plus final claims review and any retained server-backed lane proof. | Run claims matrix review and keep secure-model/live proof attached only to truly retained server-backed routes.
Not done / provider-gated unless narrowed | SMS/live texting | V2-G06 | Provider/sender/compliance/live-send proof is required before enabling/marketing. | Live proof green or SMS disabled/narrowed with no overclaims. | Provider readiness checklist or disabled-state proof.
Not done / needs proof depth | Security/privacy/data integrity | V2-G12 | Many P0 data/security micro rows are not started. | Token/service-role/upload/secret/data proofs green. | Run/repair safety and integrity proofs.
Not done / needs product proof | Photo/vault/memory delight | V2-G08 | Mobile upload/vault/recap proof and polish are not started. | Mobile upload, moderation, vault, recap proof green or narrowed. | Run mobile proof and patch rough edges.
Not done / needs final pass | Whole-product mobile/a11y/visual proof | V2-G13 | Final consumer-readiness pass still missing. | No blocking mobile, overlap, form, or visual issues remain. | Run visual/mobile matrix after core gates stabilize.

## V2 Exit Bar
DayOf V2 Consumer-Ready Exit Bar
Release rule | Do not call this V2 done because rows are marked Done. Call it V2 only when every must-pass gate below is green, every P0/P1 consumer blocker is closed, and any deferral has matching narrowed product claims.
Consumer standard | A real couple can onboard, build, publish/share, manage guests, message, collect photos, use registry/vault, and hand the experience to guests without us explaining caveats in person.
Gate ID | Gate | Must-pass definition | Evidence required | Blocks V2 if | Related tracker | Status | Closeout bucket | Can close with testing? | Still needs work / narrowing | Latest evidence
V2-G01 | Product truth and no overclaim | Marketing, owner, guest, and support copy match shipped behavior. No fake AI, SMS, custom-domain, provider, analytics, billing, or readiness claims. | Claims matrix pass, copy scan, feature audit closure. | Any public or guest-facing surface implies an unproven feature is live or fully automated. | V2-01.05, V2-21.05, V2-25.06 | In progress | Proof/narrowing | Partly: copy scan can clear shipped surfaces if green. | AI, SMS, analytics, billing, custom-domain, provider, and release-readiness claims must be proven or narrowed. | Audit found no signoff yet; keep status In progress.
V2-G02 | First-session couple wow path | A new couple can understand the product, start setup, see progress, and reach the right build/publish/share path quickly. | Signed-out and signed-in first-session desktop/mobile smoke. | The first five minutes feel like a maze, brochure, or demo instead of a working product. | V2-01.05, V2-02, V2-03 | In progress | Test-first | Yes, if signed-out and signed-in desktop/mobile first-session smoke passes. | If smoke shows maze/dead-end behavior, patch only the failing handoff/copy. | Tracker says first-session browser proof still open.
V2-G03 | Builder V2 primary path | V2 builder has a clear default/cutover path with legacy fallback, migration recovery, preview, publish/export truth, and no lab-only ambiguity. | Route/cutover tests, migration/recovery tests, owner browser smoke. | Owners are stranded between old builder and V2 lab or cannot trust which builder powers the public site. | V2-03.06 | In progress | Test-first | Mostly: automated builder gate is green; signed-in owner browser smoke remains. | If browser smoke fails, fix only builder entry/guide/legacy fallback defects. | 2026-05-28 proof:v1:builder-v2-ci-gate passed after typecheck repairs.
V2-G04 | Public V2 runtime parity | Representative V2 documents render polished public desktop/mobile pages with complete section parity, good empty/media states, metadata, and no private leaks. | Template visual proof set, public runtime tests, mobile browser proof. | A real wedding site looks placeholder, broken, inconsistent, or only schema-compatible. | V2-05.05, V2-24.05 | Not started | Actual work | No. Tests can expose the gap, but public V2 runtime parity is still marked Not started. | Build/prove V2 public renderer parity, template visual set, mobile/metadata/leak proof. | Exit Bar status Not started.
V2-G05 | Zero-friction guest journey | Invite-linked guests can RSVP, see schedule/travel, upload photos, update contact details, use registry, contribute to vault, and return later without product-internal confusion. | End-to-end mobile guest happy-path proof plus stale/invalid link recovery. | Guests hit dead ends, lose context, see token/debug wording, or need owner help for normal tasks. | V2-06.05, V2-15.05, V2-24.05 | In progress | Test-first | Partly: run guest happy-path mobile/browser proof to discover remaining failures. | Patch any token continuity, stale-link recovery, public route, or guest-safe copy failures. | Exit Bar In progress; micro V2-06.* mostly Not started.
V2-G06 | Messaging and texting truth | Lifecycle messaging is accurate; SMS is either fully provider/sender/consent/delivery proven or clearly disabled/narrowed until the API/compliance lane is ready. | Provider readiness checklist, opt-out proof, live-safe delivery readback or explicit disabled-state proof. | Texting is marketed or enabled without sender/compliance/delivery proof. | V2-10.05, V2-10.06, V2-10.07, V2-10.08 | Not started | Narrow/provider-gated | No, unless SMS remains explicitly disabled/narrowed with proof. | Do not market/enable texting until sender/compliance/delivery/opt-out proof exists; otherwise add disabled-state proof. | Exit Bar Not started; Telnyx/live SMS remains gated.
V2-G07 | AI product contract | Every AI-labeled lane is classified as model-backed, deterministic, or intentionally non-AI; model-backed claims have server-side proof, grounding, safe fallbacks, and no provider/token language. | AI readiness proof, source/grounding proof, copy audit, secure-model smoke where applicable. | The product implies model-backed intelligence where the lane is deterministic or unproven. | V2-21.05, V2-21.06, V2-21.07, V2-21.08 | In progress | Proof restored | Partly: local AI readiness proof is green again. | Cross-surface AI claims matrix and any retained server-backed lanes still need human readback and live/server proof where applicable. | 2026-05-28 restored npm run proof:v1:ai-product-readiness (7/7). Browser OpenAI key path removed; Quick Start and draft generation now prove deterministic fallback rails.
V2-G08 | Photo/vault/memory delight | Mobile photo upload, retry/progress/success/upload-more, moderation, album/recap, vault contribution, unlock continuity, and optional provider depth are polished or honestly narrowed. | Mobile upload smoke, moderation tests, vault contribution proof, recap/browser proof. | Photo or vault flows feel brittle, confusing, unsafe, or provider-dependent without honest copy. | V2-15.05, V2-15.06, V2-15.07, V2-15.08 | Not started | Work + proof | Partly after mobile photo/vault proof exists. | Polish/recover upload, retry, moderation, vault contribution, recap, and provider-depth claims or narrow them. | Exit Bar Not started.
V2-G09 | Registry public trust | Dashboard and public registry agree on purchased, partial, hidden, fund, cleanup, and thank-you-relevant state. | Public registry parity proof, registry focused suite. | Owners cannot trust that what they configured is what guests see. | V2-08.05 | In progress | Test-first | Yes, if public registry parity proof and focused suite pass. | If parity fails, patch dashboard/public purchased, fund, hidden, thank-you, and cleanup truth. | Exit Bar In progress; V2-08.05 Not started.
V2-G10 | Billing and entitlement trust | Checkout, webhooks, entitlement recovery, payment-required/success states, bypass discipline, and SMS-credit billing are proven or explicitly narrowed. | Stripe target-env/test proof, entitlement readback, recovery-copy smoke. | A paying couple can be charged, blocked, or confused by unproven billing state. | V2-19.05 | In progress | Test/narrow | Partly: entitlement/bypass/Stripe safety tests can close local truth. | Provider-backed billing proof or narrowed billing claims still needed before broad release claims. | Exit Bar In progress.
V2-G11 | Analytics and ops truth | Owner analytics and support/admin views use measured signals first and distinguish partial instrumentation from real traffic/invite/QR data. | Analytics truth tests, audit/error safe-copy scan, support diagnostics review. | The dashboard invents certainty or exposes implementation details in owner/support workflows. | V2-20.03, V2-20.05 | Not started | Proof/narrowing | No, unless analytics claims are narrowed to shipped behavior. | Owner analytics and invite-funnel truth need proof or copy removal/narrowing. | Exit Bar Not started.
V2-G12 | Security, privacy, and safe errors | Guest-facing surfaces never expose provider, token, debug, storage, database, bucket, key, service-role, or raw error language; sensitive data remains protected. | Safe-error tests, public boundary/leak scan, security proof lanes. | A normal guest or couple sees implementation/internal/security language or can access sensitive fields. | V2-20.03, V2-22, V2-25.06 | In progress | Proof-first | Partly: run safe-error, token, service-role, upload/URL, and secret-scan proofs. | Any failure needs targeted security/privacy patch before exit signoff. | Exit Bar In progress; many V2-22/V2-23 micro rows Not started.
V2-G13 | Whole-product polish | Core owner, guest, builder, coordinator, registry, messaging, photo, vault, and public-site flows pass desktop/mobile visual review for overlap, density, usability, and accessibility. | Screenshot/visual matrix, touched route browser proof, a11y spot checks. | The product works technically but feels unfinished, cramped, confusing, or visibly broken. | V2-24.05 | Not started | Release visual proof | No. Needs mobile/visual/a11y matrix after major surfaces stabilize. | Run and record whole-product visual/mobile/accessibility proof; fix blocking overlaps or guest-facing rough edges. | Exit Bar Not started.
V2-G14 | Release proof and rollback | Tracker, proof board, release notes, test results, known waivers, and rollback/V1 fallback story agree at the release candidate commit. | V2 proof board, git diff --check, focused tests, typecheck, lint, build/full tests at release boundary, release packet. | Status is stale, unverifiable, or relies on memory instead of proof. | V2-25.01, V2-25.02, V2-25.03, V2-25.04, V2-25.05, V2-25.06 | In progress | Proof infra in progress | Partly: board freshness and markdown board are green again. | Broader release-proof contract still needs reconciliation so every relied-on proof lane is real, current, and honestly scoped. | 2026-05-28 `npm run proof:v1:board:freshness` PASS and `npm run proof:v1:board:md` PASS after refreshing BACKLOG.md current-state block. ai-product-readiness was already restored in the prior batch.

## Feature Audit
DayOf Full V2 Feature Audit
Audited | 2026-05-28 16:18 PDT | Source | Tracker workbook reconciled against verified overnight/today commit batches through public truth, Builder V2 cutover proof, and customer-safe error hardening.
Priority | Area | Finding | Why it matters | Tracker coverage | Suggested next work | V2 readiness judgment
P0 | Proof, QA, Release | Tracker/proof drift is improving: Builder V2 cutover, public truth, and customer-safe hardening rows are now materially more accurate, but the workbook still needs ongoing proof-aligned updates before any V2 signoff. | Overnight work can now trust the active Builder V2 and release-proof rows more than before, but stale untouched lanes would still invite overclaiming if we stop reconciling. | V2-25.05 | Keep reconciling P0/P1 tracker rows alongside proof docs after each verified batch; do not certify V2 from stale workbook cells, and log remaining browser/env blockers explicitly. | Improving, materially better, still not release-ready.
P0 | Builder V2 Core | Builder V2 now owns /dashboard/builder and /builder with explicit guide/fallback routes, but signed owner browser smoke and legacy polish/photo escapes are still open. | Primary-path ambiguity is much lower, but V2 cannot be called closed until runtime/browser proof is logged and the remaining legacy fallback story is intentionally narrowed. | V2-03.06 | Log signed browser smoke, narrow remaining legacy fallback surfaces, and keep rollback/canary proof honest. | Core V2 blocker, materially reduced.
P0 | Public Wedding Site | V2 public runtime parity and representative visual proof are not fully proven; lab preview still has placeholder fallback states. | The builder can be schema-rich but still fail if public pages look incomplete or unsupported sections collapse. | V2-05.05 | Run desktop/mobile visual proof across representative V2 template documents and tighten empty/media states. | Core V2 blocker.
P0 | Messaging/Texting | SMS/texting is intentionally not fully live until sender, compliance, provider truth, and delivery proof are safe. | The product can support drafts and lifecycle messaging now, but cannot honestly claim fully live texting without that lane. | V2-10.05, V2-10.06, V2-10.07 | Lock provider truth, consent/opt-out UX, live-safe send proof, and delivery readback; keep guest copy free of provider/internal language. | Provider/API gated.
P0 | AI Layer | AI is real but narrow: model-backed lanes are Quick Start orchestration, photo vision, and owner site translation; several other helpers are deterministic unless server routes are added. | The product can feel smart, but public claims must not imply model-backed magic everywhere. | V2-21.05, V2-21.06, V2-21.07, V2-21.08 | Classify every AI-labeled surface, add model-backed routes only where worth it, and prove source/grounding/fallback behavior end to end. | Good foundation, needs V2 contract proof.
P1 | Photos, Vault, Memory | Guest photo upload is functional but not yet delight-grade: drag/drop, per-file progress/retry, upload-more success, event/album context, and abuse controls remain open. | Photo sharing is one of the emotional core loops; it has to feel easier than texting photos to someone. | V2-15.05, V2-15.06, V2-15.07 | Polish mobile upload, moderation, album recap, and memory follow-through with browser proof. | High-impact V2 polish gap.
P1 | Vault | Core vault contribution is real; optional Google Drive/provider continuity is narrower than core vault/archive proof. | If storage/provider depth is marketed too hard, failures feel like broken promises instead of optional integration limits. | V2-15.08 | Keep provider-specific claims narrow unless live provider proof is green; make unlock/continuity graceful either way. | Can wait if claims stay narrow.
P1 | Guest Journey | Guest-path continuity is much stronger across RSVP, contact updates, photo upload, vault contribution, and invite-linked recovery copy, but the full invite-to-RSVP-to-travel-to-photos-to-registry-to-vault mobile proof still is not logged as one journey. | Guests should never need to understand DayOf product architecture or recover from dead ends themselves. | V2-06.05 | Run a zero-friction guest happy-path proof with stale/invalid link recovery and context carry-forward. | Meaningfully reduced, still needs end-to-end proof.
P1 | Registry | Registry owner operations are substantially harder to break: imports, cleanup, maintenance, editor saves, barcode/link autofill, refresh-policy, thank-you follow-up, and shared service recovery now use safer unified copy, but public purchased-state parity proof is still open. | Couples need to trust that what they configure is what guests see, especially hide-when-purchased and thank-you follow-up. | V2-08.05 | Prove dashboard/public purchased-state parity for product gifts and funds. | Much stronger owner trust, still missing public parity proof.
P1 | Billing And Payments | Billing safety is better: shared checkout, subscription, SMS-credit, verification, and entitlement-facing error paths are now masked behind customer-safe copy, but target-environment billing proof still is not closed. | Billing failures are trust failures; vague readiness here is dangerous. | V2-19.05 | Run target-env Stripe/test proof, webhook entitlement readback, recovery copy, and SMS-credit billing truth pass. | Safer copy, proof still required.
P1 | Admin, Audit, Errors | Analytics should stick to measured signals; fuller visit/open/QR funnel instrumentation remains partial. | Owners can act on measured truth, but invented funnel certainty would damage trust. | V2-20.05 | Separate measured RSVP/registry/photo/guest-input counts from unavailable or derived invite/open/QR metrics. | Useful but not fully mature.
P1 | Customer-Safe Errors | Targeted scan still found raw err.message paths in owner/vendor/vault/messaging surfaces; guest routes are better guarded but the sweep is unfinished. | Internal/provider/storage/token/debug wording must not leak into guest-facing paths, and owner errors should still be calm/actionable. | V2-20.03 | Audit and map raw error paths through customer-safe helpers; add focused tests for meaningful changes. | Needs hardening pass.
P1 | Accessibility, Mobile, Performance | Individual flows are tested, but there is not yet a whole-product desktop/mobile visual polish matrix. | V2 holy-fuck quality is a first-impression bar, not just a unit-test bar. | V2-24.05 | Screenshot core guest, owner, builder, coordinator, memory, and public routes; fix overlap, density, dead ends, and major a11y misses. | Needed for final polish.
P2 | Vendor Profiles, Guestbook, Migration, Use-Case Packs | These are implemented or partially implemented, but not marketplace/deep-moderation/one-click-migration/full-pack mature. | They can help V2 if copy stays honest; they become risk if marketed as fully mature systems. | Existing area milestones plus claims matrix | Either narrow product copy or deepen the exact flows that are surfaced in the first V2 launch story. | Good secondary depth.
P1 | Product Entry | Public product-entry truth is materially tighter: feature pages, templates, trust/product/support/legal lanes, and signed-in CTA routing now better match shipped behavior, but first-session signed-out/signed-in browser proof is still open. | If the first five minutes are unclear, the rest of V2 depth is invisible. | V2-01.05 | Run signed-out and signed-in first-session smoke and tighten CTAs/copy around real next steps. | Much stronger, still needs wow-path proof.

## Master Milestones
ID | Area | Priority | Gap Type | Status | Current State | Full V2 Outcome | Exit Criteria | Proof Required | Owner Batch | Dependencies
V2-01 | Product Entry | P1 | Depth | In progress | Public entry truth and CTA continuity are materially better across feature pages, templates, trust/product, and support/legal surfaces; first-session browser proof is still open. | Public entry routes explain the real product, route signed-in users to live work, and avoid overclaiming. | Home, Product, Trust, feature pages, Templates, VendorProfile, support/legal/refund/auth routes share one promise and tested CTA behavior. | Focused route tests, signed-in/signed-out CTA smoke, copy leak scan. | Public entry batch | None
V2-02 | Auth And Onboarding | P1 | Depth | In progress | Auth/onboarding continuation and first-session safety are stronger, with clearer setup handoff and safer GuidedSetup/Onboarding recovery copy, but the funnel still needs unified browser proof. | Every start path resumes safely, recovers malformed state, and produces useful setup truth for the rest of the app. | Signup/login continuation, OAuth return, saved draft restore, AI follow-ups, and Celebration handoff are unified and tested. | Onboarding focused tests, auth continuation tests, malformed state recovery tests. | Onboarding spine batch | Product Entry
V2-03 | Builder V2 Core | P0 | Actual | In progress | Automated Builder V2 CI gate is green as of 2026-05-28 after typecheck/test fixture repair; signed-in owner browser smoke and public-runtime handoff are still open, so status stays In progress. | Builder V2 has locked schema, multi-page editing, public runtime, migration, recovery, and release proof. | V2 can create, edit, preview, publish, recover, export, and render a real multi-page wedding site. | Builder V2 tests, public runtime tests, browser smoke, migration proof. | Builder V2 release batch | Templates And Variants, Public Wedding Site
V2-04 | Templates And Variants | P0 | Actual | Not started | Template chooser improved; long-tail variant/import compatibility still needs V2-grade proof. | Templates are V2-native, comparable, partially applicable, visually proven, and migration-safe. | Every shipped template imports into V2, renders publicly, passes compatibility checks, and has visual/sample data proof. | Template matrix tests, variant compatibility tests, visual proof set. | Template system batch | Builder V2 Core
V2-05 | Public Wedding Site | P0 | Actual | Not started | Current public runtime exists, but V2 document runtime parity remains Not started in the tracker and blocks V2 until proven with mobile/template/leak evidence. | V2 documents render guest-safe, mobile-first, performant public sites with complete section parity. | All canonical sections render from V2 docs with no private leaks, strong empty states, metadata, and mobile proof. | Public runtime tests, mobile browser smoke, SEO/share checks, leak scan. | V2 runtime batch | Builder V2 Core, Templates And Variants
V2-06 | Guest Journey | P1 | Depth | Not started | Guest journey companion is strong; all guest tools need end-to-end V2 continuity proof. | Guests move through RSVP, travel, photos, contact, vault, and keepsake paths without friction or ops leakage. | Guest companion, public routes, token continuity, stale-link recovery, and mobile flows behave as one system. | Guest route tests, token stale/invalid tests, mobile smoke. | Guest spine batch | Public Wedding Site
V2-07 | RSVP And Event RSVP | P1 | Depth | In progress | Main RSVP, Event RSVP, and embedded RSVP sections now share calmer guest-safe recovery semantics more consistently, but full RSVP operating-system proof is still open. | Attendance, deadline, meal, dietary, group, and event RSVP states feed guest, owner, coordinator, and messaging truth. | Main RSVP and Event RSVP share status semantics, prevent stale overwrite, and drive dashboard/coordinator/messaging outputs. | RSVP full route tests, event RSVP sync tests, proof:v1 guests-rsvp-ops. | RSVP truth batch | Guest Journey
V2-08 | Registry | P1 | Depth | In progress | Registry owner operations and service recovery are materially harder to break, but dashboard/public purchased-state parity proof and end-to-end registry confidence still remain open. | Owner setup, imports, cleanup, duplicates, funds, guest purchase, refresh, and thank-yous operate as one registry system. | Registry dashboard and public registry section stay synchronized through import, refresh, cleanup, purchase, and thank-you flows. | Registry focused suite, proof:v1 registry, public section smoke. | Registry operating system batch | Public Wedding Site, Guest Journey
V2-09 | Guests And Contact Management | P1 | Depth | In progress | Guest/contact operations and public contact-update recovery are safer and more coherent, but the full owner CRUD/import/readiness pass still needs proof. | Guest list, household/group state, contact update, RSVP state, and messaging readiness are one reliable owner workflow. | Owners can import/edit/export guests, understand missing contact data, and route guests into the right update/RSVP flows. | Guest ops tests, contact update tests, CSV/import tests. | Guest ops batch | RSVP And Event RSVP, Messaging
V2-10 | Messaging | P1 | Depth | In progress | Messaging recovery paths are safer and owner copy is calmer, but provider/sender/compliance/live-delivery proof is still the gating issue. | Templates, variables, scheduled sends, email/SMS, history, targeting, preview, compliance, and delivery recovery feel safe and coherent. | Every send has preview, audience clarity, consent/compliance truth, delivery state, and failed/partial recovery. | Comms focused tests, proof:v1 comms-center, live SMS proof, secret-safe UI scan. | Messaging reliability batch | Guests And Contact Management
V2-11 | Planning | P1 | Depth | Not started | Planning guidance is polished; tasks, vendors, ownership, and reminders need deeper connective tissue. | Planning becomes a real assistant across tasks, vendors, decisions, timelines, owner/planner roles, and next actions. | Planning recommendations route to concrete actions and preserve ownership, reminder, and collaborator truth. | Planning focused tests, vendor tests, planner handoff tests. | Planning brain batch | Collaborators And Permissions
V2-12 | Itinerary And Travel | P1 | Depth | Not started | Itinerary readiness is strong; travel/venue/schedule data needs one authoritative truth pass. | Owner itinerary, public schedule, travel/accommodations, venue data, and coordinator timing all align. | Date/time, venue, travel, and public schedule data resolve consistently across owner, guest, and coordinator surfaces. | Itinerary date/time tests, public schedule tests, travel section smoke. | Itinerary truth batch | Public Wedding Site, Coordinator And Day-Of
V2-13 | Seating | P1 | Depth | Not started | Seating guidance is better; operational constraints and handoff need deeper feature completeness. | Seating supports guest groups, constraints, tables, unresolved issues, coordinator handoff, and export readiness. | Owner can identify seating blockers, act on constraints, and hand off room truth to coordinator/venue staff. | Seating focused tests, coordinator integration tests, export/handoff check. | Seating operations batch | Guests And Contact Management, Coordinator And Day-Of
V2-14 | Coordinator And Day-Of | P0 | Depth | Not started | Coordinator/day-of surfaces are upgraded; full command-center cohesion still needs proof and action depth. | Coordinator mode handles alerts, Q&A, corrections, check-ins, timeline, relay, dispatch, seating, and guest issues live. | Every day-of signal has priority, owner, suggested action, manual override, resolution, and mobile-friendly flow. | Coordinator focused tests, proof:v1 coordinator-dayof, mobile smoke. | Day-of command batch | Messaging, RSVP And Event RSVP, Itinerary And Travel, Seating
V2-15 | Photos, Vault, Memory | P2 | Depth | In progress | Photo upload, vault contribution, and memory recovery states are safer and more truthful, but mobile upload delight and deeper polish/proof remain open. | Photo upload, albums, vault contributions, moderation, recap, memory curation, keepsake, and export are one premium memory workflow. | Guests can contribute easily; owners can review, curate, publish, and export without confusing privacy boundaries or clunky mobile steps. | Photo/vault safety tests, guest mobile upload smoke, vault provider proof, export check. | Memory system batch | Guest Journey, Public Wedding Site
V2-16 | Name Change | P2 | Depth | Not started | Feature is unusually deep; V2 pass should focus on coherence, recovery, and proof rather than raw capability. | Planner, execution, reminders, target vault, forms, packets, proof, and resume paths feel like one serious assistant. | Users always know current status, next proof need, target dependency, and resume path across all name-change surfaces. | Name-change focused suite, form/packet tests, planner route smoke. | Name-change assistant batch | Planning
V2-17 | Collaborators And Permissions | P1 | Depth | Not started | Role framing is strong; enforcement, audit, and edge-case invitation flows need full-product proof. | Owners, planners, coordinators, and viewers each have clear capabilities, safe invites, and understandable permission failures. | Invite acceptance, signup continuation, saved local setup, pending invites, access checks, and role UI all agree. | Collaborator access tests, proof:v1 collaborator-access, permission denial tests. | Collaboration trust batch | Settings And Identity
V2-18 | Settings And Identity | P1 | Depth | Not started | Settings guidance is stronger; site access, identity export, and dangerous settings need deeper trust work. | Settings feels like a safe control room for privacy, access, identity, collaborators, site switching, and exports. | Public/password/invite states, collaborator setup, identity exports, site select, and dangerous actions have clear recovery. | Settings tests, site access tests, identity export tests. | Settings trust batch | Collaborators And Permissions
V2-19 | Billing And Payments | P2 | Proof | Not started | Payment flows exist with safety coverage; product-grade billing clarity and bypass discipline need proof. | Payment required/success, checkout, subscription, SMS credits, and bypass/test states are clear and safe. | No guest-facing billing leaks, checkout/session paths are verified, bypass is controlled, and recovery copy is friendly. | Stripe safety tests, payment route smoke, bypass cleanup checks. | Billing trust batch | Settings And Identity
V2-20 | Admin, Audit, Errors | P2 | Actual | Not started | AuditLogs and ErrorLogs exist but need to become truly useful and customer-safe. | Internal operators can understand actions/errors without exposing secrets or confusing customers. | Audit logs, error logs, safe errors, support context, and recovery states are readable and secret-safe. | Audit/error tests, safe error scans, no-secret UI review. | Ops visibility batch | Security And Privacy
V2-21 | AI Layer | P1 | Depth | Not started | Local AI readiness proof is restored and green again, and browser-side OpenAI key usage is removed in favor of deterministic fallback/server-only key paths. The AI gate remains In progress until cross-surface claims and any retained server-backed lanes are fully reconciled. | AI suggestions preview before apply, respect user edits, express uncertainty, ground recommendations in current data, and clearly separate model-backed vs deterministic help. | Every marketed AI lane is reviewable, grounded, safe, and honestly proven end to end. | AI focused tests, user-edit preservation tests, browser/mobile AI proof, internal-leak scan. | AI trust batch | Auth And Onboarding, Builder V2 Core
V2-22 | Data Integrity | P0 | Proof | Not started | Many integrity helpers exist; full-product integrity sweep needs central ownership and proof. | Canonical adapters, hydration, imports, exports, migration, stale state cleanup, and integrity reports agree. | Registry, builder, RSVP, guest, planning, and public runtime data can be swept, repaired, and reported safely. | Integrity sweep tests, import/export tests, proof:v1 data-integrity. | Data integrity batch | Builder V2 Core, Registry, RSVP And Event RSVP
V2-23 | Security And Privacy | P0 | Proof | Not started | Safety tests exist; full-product V2 needs a deliberate privacy/security pass before release. | Tokens, private data, uploads, URLs, service-role paths, logs, and docs are secret-safe and guest-safe. | No secrets or internal diagnostics leak; guest/private boundaries are tested; upload/url safety is verified. | Security focused tests, leak scan, service-role authorization proof when available. | Security release batch | Data Integrity
V2-24 | Accessibility, Mobile, Performance | P1 | Proof | Not started | Individual flows work; whole-product mobile/accessibility/performance proof is not complete. | Major guest, owner, coordinator, and builder flows are mobile-safe, keyboard-safe, screen-reader sane, and fast enough. | No major layout overlap, unusable mobile controls, inaccessible core forms, or public performance regressions remain. | Mobile browser smoke, a11y spot checks, build/perf scan. | Experience proof batch | Public Wedding Site, Builder V2 Core, Coordinator And Day-Of
V2-25 | Proof, QA, Release | P0 | Proof | Not started | Tracker/proof reconciliation is still in progress, but two concrete proof-infra gaps are repaired: ai-product-readiness is restored and proof-board freshness is green again. The remaining release-proof contract cleanup is narrower and still open. | Every V2 release candidate has proof scripts, browser smoke, docs, rollback notes, honest gate status, and a green consumer-ready exit bar before V2 is called done. | V2 proof board is current, milestone gates are green or explicitly narrowed, release notes match shipped truth, and all P0/P1 consumer-ready gates are Done or intentionally deferred with product claims narrowed. | proof:v1 board refresh, V2 proof scripts, branch-level audit, V2 Exit Bar readback, visual proof matrix. | Release truth batch | All P0/P1 product milestones

## Micro Milestones
ID | Area | Micro Milestone | Gap Type | Priority | Definition Of Done | Exit Criteria | Primary Files | Tests / Proof | Status | Notes
V2-01.01 | Product Entry | Signed-in CTA routing | Depth | P1 | Home/Product/Trust CTAs route signed-in users to live workspaces and anonymous users to signup. | Route tests cover signed-in and anonymous paths; no dead marketing loop remains. | Home.tsx, Product.tsx, Trust.tsx | Route tests, CTA smoke | In progress | Signed-in CTA routing is improved across feature and template decision surfaces; home/product/trust/browser proof still remains.
V2-01.02 | Product Entry | Feature page truth pass | Depth | P2 | Feature pages describe real shipped workflows without fake automation claims. | Copy scan passes; every CTA routes to a real next step. | src/pages/features | Copy review, route smoke | Done | Feature page truth and CTA continuity were tightened and tested; signed-in users route into real workspaces and dead /features routing was removed.
V2-01.03 | Product Entry | Template/vendor public decision surfaces | Depth | P2 | Templates and VendorProfile help a user decide, compare, and act. | Search/compare/decision guidance covered by tests; no static brochure dead ends. | Templates.tsx, VendorProfile.tsx | Focused tests | In progress | Template decision surfaces are much stronger and signed-in template CTAs route into Builder V2, but VendorProfile still needs a fuller decision-surface pass.
V2-01.04 | Product Entry | Support/legal/refund finish | Proof | P2 | Support, Privacy, Terms, Refund, auth support links feel complete and consistent. | All legal/support links resolve and copy is customer-safe. | Support.tsx, Privacy.tsx, Terms.tsx, Refund.tsx | Route smoke, link check | Done | Support, privacy, terms, refund, and auth support continuity were aligned and route-tested.
V2-01.05 | Product Entry | First-session wow path | Depth | P1 | The first signed-out and signed-in session routes a couple to a useful setup/build/publish next step within minutes, with no fake readiness claims. | A new couple can understand the product, start the right path, and see credible progress without needing a tour from us. | Home.tsx, Product.tsx, Onboarding, Setup, Builder V2 | First-session route smoke | In progress | Copy and CTA truth improved across public entry and onboarding, but signed-out and signed-in first-session browser smoke is still open.
V2-02.01 | Auth And Onboarding | Continuation safety | Depth | P1 | Signup/login/OAuth preserve and clean setup state across interruptions. | Malformed and stale state recovery tests pass. | Signup.tsx, Login.tsx, signupContinuation.ts | Continuation tests | In progress | Continuation/auth handoff safety improved across signup/login/onboarding flows, but the full malformed-state continuation lane is not yet fully proven.
V2-02.02 | Auth And Onboarding | QuickStart to GuidedSetup spine | Depth | P1 | QuickStart, GuidedSetup, Onboarding, WeddingStatus, Celebration feel like one funnel. | All transitions have clear current/next state and no duplicate stale storage. | src/pages/onboarding | Onboarding route tests | In progress | QuickStart, GuidedSetup, and onboarding recovery paths are safer and clearer, but the full funnel still needs one unified proof pass.
V2-02.03 | Auth And Onboarding | AI follow-up quality | Depth | P1 | AI follow-ups ask useful missing-context questions and avoid junk prompts. | Evaluation fixtures pass; thin data gets honest fallback. | aiFollowUpPlanner.ts, aiOnboarding.ts | AI tests | Not started
V2-02.04 | Auth And Onboarding | Setup-to-V2 handoff | Actual | P0 | Setup draft output maps directly into Builder V2 document/profile truth. | Generated setup can seed a V2 doc with no manual bridge work. | setupDraft.ts, BuilderV2Lab.tsx | Adapter tests | Not started
V2-03.01 | Builder V2 Core | Schema lock | Actual | P0 | Document schema/version contract is explicit and validated. | All V2 documents carry version metadata and validate with actionable errors. | builder-v2/contracts.ts, validate.ts | Schema tests | Not started
V2-03.02 | Builder V2 Core | Multi-page model | Actual | P0 | V2 supports pages, slugs, nav visibility, home page, and page health. | Users can add/rename/remove/reorder pages without slug or home-page drift. | BuilderV2Lab.tsx, builder-v2 | Focused tests | Not started
V2-03.03 | Builder V2 Core | Section/block editing completeness | Actual | P0 | Sections and blocks can be added, edited, moved, duplicated, hidden, restored, and removed. | Each action has tests and preserves valid selection/recovery state. | BuilderV2Lab.tsx, builderV2* models | Editor tests | Not started
V2-03.04 | Builder V2 Core | Undo and checkpoints | Actual | P0 | V2 has undo/redo and named restore checkpoints. | Any destructive action creates or preserves a recoverable point. | BuilderV2Lab.tsx | Checkpoint tests | Not started
V2-03.05 | Builder V2 Core | Preview and launch gate | Actual | P0 | Preview mode and launch checklist use V2 document health. | Every blocker routes to exact fix; preview verifies desktop/mobile. | BuilderV2Lab.tsx | Preview/launch tests | Not started
V2-03.06 | Builder V2 Core | Default builder cutover path | Actual | P0 | Builder V2 has a clear route to become the primary builder, with legacy fallback, migration recovery, and user-facing cutover truth. | Owners are not stranded between old builder and V2 lab when creating, editing, previewing, or publishing a real site. | BuilderV2Lab.tsx, BuilderPage.tsx, routes, migration adapter | Cutover tests and smoke | In progress | Primary builder routes are promoted to /dashboard/builder and /builder with explicit guide/fallback/rollback/import-export proof. Still open: signed browser smoke and remaining legacy photo/polish escapes.
V2-04.01 | Templates And Variants | V2-native template catalog | Actual | P0 | Templates can instantiate real V2 documents. | Every template creates a valid V2 doc with starter content. | Templates.tsx, sections | Template generation tests | Not started
V2-04.02 | Templates And Variants | Template compare and partial apply | Depth | P1 | Users can compare templates and apply page/section packs without wiping good work. | Apply preview shows impact and rollback point. | Templates.tsx, BuilderV2Lab.tsx | Compare/apply tests | Not started
V2-04.03 | Templates And Variants | Variant compatibility matrix | Proof | P0 | Every shipped variant renders in V1 and V2 paths or has a migration note. | Matrix test covers canonical variants and legacy aliases. | src/sections, builder-v2 | Compatibility tests | Not started
V2-04.04 | Templates And Variants | Template visual proof | Proof | P1 | Representative templates have mobile/desktop screenshots. | No obvious overlap, blank section, or broken image in proof set. | Template preview routes | Browser proof | Not started
V2-05.01 | Public Wedding Site | V2 runtime renderer | Actual | P0 | V2 documents render public pages directly. | All canonical section types render from V2 contracts. | SiteView.tsx, sections | Runtime tests | Not started
V2-05.02 | Public Wedding Site | Guest-safe private boundary | Proof | P0 | Hidden/private/internal fields never appear publicly. | Leak scan passes for token, provider, bucket, command, internal errors. | SiteView.tsx, sections | Leak scan | Not started
V2-05.03 | Public Wedding Site | SEO and sharing | Depth | P1 | V2 public sites generate metadata/share cards from wedding truth. | Title, description, canonical URL, and preview image resolve safely. | SiteView.tsx | SEO smoke | Not started
V2-05.04 | Public Wedding Site | Archive and keepsake mode | Depth | P2 | Public site can transition after wedding into keepsake/archive state. | Archive mode changes calls-to-action and hides stale operational prompts. | archiveMode.ts, SiteView.tsx | Archive tests | Not started
V2-05.05 | Public Wedding Site | V2 public visual parity matrix | Proof | P0 | Representative V2 documents from real templates render public desktop/mobile pages with expected sections, spacing, media, metadata, and empty states. | The public V2 runtime is visually believable, not just schema-compatible. | V2 runtime, templates, SiteView.tsx | Template visual proof set | Not started | Audit-derived V2 readiness gap.
V2-06.01 | Guest Journey | Guest companion spine | Depth | P1 | GuestJourneyCompanion appears where useful and never repeats current surface. | Next-step links are contextual and tested across RSVP/photo/contact/vault. | GuestJourneyCompanion.tsx | Guest tests | Not started
V2-06.02 | Guest Journey | Token continuity | Depth | P1 | Guest token state persists correctly and recovers from stale/invalid links. | Invalid/stale tokens produce friendly recovery, not broken forms. | RSVP.tsx, EventRSVP.tsx | Token tests | Not started
V2-06.03 | Guest Journey | Mobile guest proof | Proof | P1 | Guest RSVP, photo, contact, vault, and registry routes work on mobile. | No critical mobile layout blockers in route smoke. | Guest routes | Mobile smoke | Not started
V2-06.04 | Guest Journey | No ops leakage | Proof | P0 | Guest surfaces never show internal ops wording or debug truth. | Leak scan passes across guest routes. | Guest routes | Copy leak scan | Not started
V2-06.05 | Guest Journey | Zero-friction guest happy path | Depth | P1 | A guest can move from invite link to RSVP, schedule/travel, photo upload, contact update, registry, vault, and recap without confusing branching or dead ends. | The guest path feels obvious on mobile and carries context forward without making guests understand product internals. | GuestJourneyCompanion.tsx, public guest routes | Guest happy-path browser proof | Not started | Audit-derived V2 readiness gap.
V2-07.01 | RSVP And Event RSVP | Unified RSVP semantics | Depth | P1 | Main RSVP and per-event RSVP share status, attendance, and support semantics. | Dashboard and public views interpret the same RSVP truth consistently. | RSVP.tsx, EventRSVP.tsx | RSVP tests | In progress | Main RSVP, Event RSVP, and embedded RSVP flows now share more consistent guest-safe error semantics; broader semantic parity proof remains open.
V2-07.02 | RSVP And Event RSVP | Group and partial RSVP | Depth | P1 | Household/group RSVP handles mixed attendance and partial submissions. | Partial edits do not erase other guest intent. | RSVP.tsx | Group RSVP tests | Not started
V2-07.03 | RSVP And Event RSVP | Meal and accessibility notes | Depth | P2 | Meal, dietary, accessibility, and notes are collected and surfaced safely. | Owner/coordinator views show useful notes without public leaks. | dietaryNotes.ts, RsvpBoard.tsx | Notes tests | Not started
V2-07.04 | RSVP And Event RSVP | RSVP proof script | Proof | P1 | Existing RSVP proof script covers the V2 public flow. | proof:v1 guests-rsvp-ops passes or V2 successor exists. | proof scripts | Proof command | Not started
V2-08.01 | Registry | Owner import/cleanup flow | Depth | P1 | Import, cleanup, repair, and duplicate review feel like one owner workflow. | Owner can recover bad imports and resolve duplicates with visible proof. | RegistryDashboardRouteContent.tsx | Registry tests | In progress | Owner import, cleanup, duplicate review, and maintenance recovery paths are much stronger and better tested.
V2-08.02 | Registry | Cash fund trust | Depth | P1 | Cash funds expose safe contribution methods and owner setup gaps clearly. | Guest never sees unsupported contribution state as ready. | RegistrySection.tsx | Cash fund tests | Not started
V2-08.03 | Registry | Refresh and canonical truth | Proof | P1 | Canonical URL, barcode, refresh, and owner-edited truth do not fight. | Refresh never overwrites manual owner intent incorrectly. | registryService.ts | Refresh tests | In progress | Refresh, canonical truth, link autofill, and barcode lookup recovery now route through unified registry-safe copy and service tests.
V2-08.04 | Registry | Thank-you workflow | Depth | P2 | Purchaser tracking and thank-you tasks are operationally useful. | Missing purchaser, completed thank-you, and follow-up states are clear. | registry | Thank-you tests | Not started
V2-08.05 | Registry | Public purchased-state parity | Proof | P1 | Dashboard purchased/hidden/claimed truth mirrors public registry behavior across product gifts and funds. | Owners can trust that hide-when-purchased and thank-you state match what guests actually see. | Registry.tsx, RegistrySection.tsx, registry services | Public registry parity proof | Not started | Audit-derived V2 readiness gap.
V2-09.01 | Guests And Contact Management | Guest list CRUD polish | Depth | P1 | Guest add/edit/delete/search/filter states are clean and recoverable. | Owner can safely manage a real list without stale UI states. | Guests.tsx | Guest ops tests | Not started
V2-09.02 | Guests And Contact Management | Contact update flow | Depth | P1 | Guests can update contact info through a safe public path. | Owner sees contact freshness and can request updates. | GuestContactUpdate.tsx | Contact tests | In progress | Guest contact-update public recovery is safer and invite-linked continuity is stronger, but the full owner freshness loop still needs proof.
V2-09.03 | Guests And Contact Management | CSV import/export safety | Actual | P1 | CSV import/export handles headers, bad rows, and duplicates. | Bad imports produce repairable reports, not silent corruption. | csvHeaderMatcher.ts, Guests.tsx | CSV tests | Not started
V2-09.04 | Guests And Contact Management | Messaging readiness | Depth | P1 | Guest contact and RSVP state produce clear message-ready segments. | Messaging cannot send to unclear audiences without review. | Guests.tsx, Messages.tsx | Integration tests | Not started
V2-10.01 | Messaging | Preview before send | Depth | P0 | Every bulk/scheduled message has preview and variable validation before send. | No send path bypasses audience and variable review. | Messages.tsx | Comms tests | Not started
V2-10.02 | Messaging | Audience targeting clarity | Depth | P1 | Audience segments are named, counted, and explainable. | Owners can see exactly who receives a message. | Messages.tsx | Audience tests | Not started
V2-10.03 | Messaging | Delivery recovery | Actual | P1 | Failed/partial delivery states route to retry or alternate action. | Message history surfaces failed, skipped, sent, and pending states clearly. | messageDeliveryState.ts | Delivery tests | In progress | Delivery and dispatch recovery copy is safer across messaging helpers and workspace load/retry paths, but end-to-end delivery proof remains open.
V2-10.04 | Messaging | SMS compliance lock | Proof | P0 | Live SMS remains locked until compliance is explicitly ready. | No UI implies live SMS works before Telnyx/A2P setup. | Messages.tsx | Compliance scan | Not started
V2-10.05 | Messaging | SMS provider truth and sender readiness | Proof | P0 | The canonical SMS provider, sender setup, env contract, and rollout docs agree with the live runtime path. | No mixed Telnyx/Twilio/provider truth remains before texting is enabled. | send-bulk-message, SMS docs, env helpers | Provider readiness checklist | Not started | Endgame-critical for V2 holy-fuck bar.
V2-10.06 | Messaging | Consent, opt-out, and compliance UX | Depth | P0 | Phone capture, consent copy, unsubscribe/STOP behavior, and owner warnings are explicit across guest and owner flows. | No live texting path can be enabled without guest-safe consent and compliance behavior. | Messages.tsx, Guests.tsx, guest contact flows | Compliance and opt-out tests | Not started | Endgame-critical for V2 holy-fuck bar.
V2-10.07 | Messaging | Live send and delivery proof | Proof | P0 | Allowlisted provider-backed sends prove create, dispatch, delivery readback, failure grouping, and retry behavior. | A real SMS can be sent, traced, retried, and audited without secret leakage. | send-bulk-message, message delivery logs | Live SMS proof | Not started | Endgame-critical for V2 holy-fuck bar.
V2-10.08 | Messaging | SMS credits and billing reconciliation | Actual | P1 | Credit purchase, balance changes, send deduction, expiry, and recovery copy reconcile exactly with the runtime ledger. | Texting can be billed and reasoned about without hidden credit drift or confusing owner state. | Billing routes, sms credits tables, Messages.tsx | Billing and credit proof | Not started | Nice-to-have if racing; becomes critical if SMS credits ship in the first V2 push.
V2-11.01 | Planning | Task and ownership truth | Depth | P1 | Tasks, owners, due dates, and planner roles agree. | Planner and owner views do not conflict on responsibility. | Planning.tsx | Planning tests | Not started
V2-11.02 | Planning | Vendor decision depth | Depth | P1 | Vendor comparison supports risk, fit, next ask, and public/vendor profile handoff. | Vendor cards route to concrete decision actions. | vendorDecisionSupport.ts | Vendor tests | Not started
V2-11.03 | Planning | Reminder integration | Depth | P2 | Planning reminders surface without creating duplicate or stale pressure. | Reminder timing and execution status agree. | planning | Reminder tests | Not started
V2-11.04 | Planning | Planner handoff proof | Proof | P1 | Planner/coordinator/viewer handoff card remains accurate across role modes. | Role-specific next moves and watchouts match capabilities. | PlannerHandoffCard.tsx | Role tests | Not started
V2-12.01 | Itinerary And Travel | Authoritative event model | Depth | P1 | Itinerary events feed public schedule, guest event RSVP, and coordinator timing. | Changing an event updates all relevant reads. | Itinerary.tsx | Event model tests | Not started
V2-12.02 | Itinerary And Travel | Travel/accommodations truth | Depth | P1 | Travel, accommodations, venue, and schedule sections share source truth. | Public travel copy never contradicts owner dashboard data. | TravelSection.tsx | Section tests | Not started
V2-12.03 | Itinerary And Travel | Date/time safety | Proof | P0 | Invalid dates/times never render broken guest or owner UI. | Date helper tests cover dashboard/public paths. | itineraryDateTime.ts | Date tests | Not started
V2-12.04 | Itinerary And Travel | Coordinator timing handoff | Depth | P1 | Coordinator mode consumes itinerary timing cleanly. | Day-of timeline does not drift from owner itinerary. | CoordinatorMode.tsx | Coordinator tests | Not started
V2-13.01 | Seating | Constraint model | Actual | P1 | Seating constraints are explicit and visible to owners. | Unresolved constraints appear in seating guidance. | seatingService.ts | Seating tests | Not started
V2-13.02 | Seating | Table and group operations | Depth | P1 | Tables, groups, and assignments can be managed without hidden drift. | Owner can identify unassigned guests and group conflicts. | Seating.tsx | Seating UI tests | Not started
V2-13.03 | Seating | Seating handoff export | Actual | P2 | Seating truth can be handed off to coordinator/venue staff. | Export packet includes tables, issues, and notes. | Seating.tsx | Export tests | Not started
V2-13.04 | Seating | Coordinator seating bridge | Depth | P1 | Coordinator sees seating blockers and day-of relevance. | Seating changes can become coordinator actions when needed. | CoordinatorMode.tsx | Integration tests | Not started
V2-14.01 | Coordinator And Day-Of | Unified command queue | Depth | P0 | Alerts, Q&A, corrections, check-ins, timeline, and relay share priority logic. | Coordinator mode shows one clear action queue. | CoordinatorMode.tsx | Coordinator tests | Not started
V2-14.02 | Coordinator And Day-Of | Manual override safety | Depth | P1 | Manual overrides have clear reason, expiry, reset, and target labeling. | Overrides cannot quietly persist past usefulness. | coordinator*Override*.ts | Override tests | Not started
V2-14.03 | Coordinator And Day-Of | Mobile day-of cockpit | Proof | P0 | Coordinator mode is usable on phone during live event. | Primary actions fit, no overlap, no desktop-only dependency. | CoordinatorMode.tsx | Mobile smoke | Not started
V2-14.04 | Coordinator And Day-Of | Dispatch and messaging bridge | Depth | P1 | Day-of dispatch turns live issues into safe messages. | Dispatch recommendations preview audience and message before send. | dayOfDispatch.ts, Messages.tsx | Dispatch tests | Not started
V2-15.01 | Photos, Vault, Memory | Guest upload trust | Depth | P1 | Guest photo upload handles failures, moderation, and privacy clearly. | Guests can upload without seeing storage/internal errors. | PhotoUpload.tsx | Upload tests | In progress | Guest upload trust is materially better across photo upload and vault contribution recovery states, but delight-grade mobile proof is still open.
V2-15.02 | Photos, Vault, Memory | Album management | Actual | P2 | Owners can organize, hide, and manage albums cleanly. | Album create/manage safety tests cover main flows. | GuestPhotoSharing.tsx | Album tests | Not started
V2-15.03 | Photos, Vault, Memory | Memory curation workflow | Depth | P2 | MemoryCurator becomes a real editorial workflow with next actions and export. | Curator guidance routes to concrete review/publish/export actions. | MemoryCuratorCard.tsx | Memory tests | Not started
V2-15.04 | Photos, Vault, Memory | Vault and keepsake export | Depth | P2 | Vault contributions can be reviewed and exported for keepsake mode. | No private/unreviewed content leaks publicly. | Vault.tsx, VaultContribute.tsx | Vault tests | Not started
V2-15.05 | Photos, Vault, Memory | Mobile guest upload delight | Depth | P1 | Guest upload on phone has clear progress, retry, success, and upload-more follow-through with event/album context. | Guests can contribute from mobile without confusion, dead ends, or stale feedback. | PhotoUpload.tsx, GuestPhotoSharing.tsx | Mobile upload smoke | Not started | Endgame-critical for V2 holy-fuck bar.
V2-15.06 | Photos, Vault, Memory | Moderation and abuse controls | Proof | P1 | Velocity limits, moderation states, and uploader safety controls are explicit and proven on public memory routes. | Owners can trust public uploads without guessing whether unsafe or spammy content is contained. | photo-upload function, GuestPhotoSharing.tsx, VaultContribute.tsx | Upload safety proof | Not started | Endgame-critical for V2 holy-fuck bar.
V2-15.07 | Photos, Vault, Memory | Album and recap polish | Depth | P1 | Album cover choice, title stability, recap continuity, and upload-to-recap follow-through feel like one polished memory surface. | Owner memory workflow reads as premium instead of a set of adjacent utilities. | GuestPhotoSharing.tsx, EventRecap.tsx | Album and recap tests | Not started | Nice-to-have if racing.
V2-15.08 | Photos, Vault, Memory | Vault provider depth and unlock continuity | Proof | P1 | If provider-backed vault depth stays in scope, the full connect, upload, unlock, and export cycle is live-proven and guest-safe. | Vault promises are either fully proven or honestly narrowed with no fuzzy staged-rollout gap. | Vault.tsx, VaultContribute.tsx, Drive callbacks | Vault provider proof | Not started | Can wait until after first real V2 launch push only if provider-backed vault depth stays explicitly narrowed in product claims.
V2-16.01 | Name Change | Resume path coherence | Depth | P2 | Overview, planning, and planner tab resume into the same target truth. | All resume links land at useful current status. | NameChangePlannerTab.tsx | Name-change tests | Not started
V2-16.02 | Name Change | Proof readiness clarity | Depth | P2 | Every target shows proof need, blocker, next ask, and dependency. | No target card has ambiguous ready/blocked wording. | nameChange | Target tests | Not started
V2-16.03 | Name Change | Forms and packets | Depth | P2 | Forms, PDF/FDF, packets, companion intake, and secure sessions are aligned. | Generated packets include correct target context and safe review copy. | src/lib/nameChange | Form tests | Not started
V2-16.04 | Name Change | Reminder and execution status | Proof | P2 | Reminder timing and execution status do not conflict. | Latest movement and proof debt stay visible. | NameChangePlannerTab.tsx | Focused suite | Not started
V2-17.01 | Collaborators And Permissions | Invite acceptance edge cases | Depth | P1 | Accept invite handles invalid, expired, pending, and existing-user states. | Every error has useful next action. | AcceptCollaboratorInvite.tsx | Invite tests | Not started
V2-17.02 | Collaborators And Permissions | Role enforcement | Proof | P0 | Owner/planner/coordinator/viewer capabilities are enforced, not just described. | Forbidden actions fail friendly and log safely. | plannerAccess.ts, dashboardRoleGuide.ts | Access tests | Not started
V2-17.03 | Collaborators And Permissions | Pending invite management | Depth | P1 | Settings makes pending and saved-local collaborator setup clear. | Owners can understand and clean up pending access state. | Settings.tsx | Settings tests | Not started
V2-17.04 | Collaborators And Permissions | Audit trail bridge | Actual | P2 | Collaborator changes write useful audit trail entries. | Audit log shows who changed role/access without secret leakage. | AuditLogs.tsx, actionAudit.ts | Audit tests | Not started
V2-18.01 | Settings And Identity | Access mode safety | Depth | P1 | Public/password/invite-only access modes are clear and hard to misconfigure. | Changing access mode shows consequences and recovery. | siteAccessPlan.ts, Settings.tsx | Access tests | Not started
V2-18.02 | Settings And Identity | Identity export handoff | Depth | P1 | Identity exports are packaged with warnings, purpose, and next steps. | Export kit produces useful files/copy without overexposing private data. | SettingsIdentityExportsPanel.tsx | Export tests | Not started
V2-18.03 | Settings And Identity | Site switching safety | Proof | P1 | Multi-site selection cannot cross-wire dashboard actions. | Selected site state is visible and safely persisted. | settingsSiteSelect.ts | Site select tests | Not started
V2-18.04 | Settings And Identity | Dangerous action confirmations | Actual | P2 | Destructive settings require confirmation and recovery copy. | No dangerous setting can be triggered by ambiguous click. | Settings.tsx | UI tests | Not started
V2-19.01 | Billing And Payments | Checkout flow clarity | Proof | P2 | PaymentRequired and PaymentSuccess clearly explain status and next step. | Payment routes do not strand users or leak internal state. | PaymentRequired.tsx, PaymentSuccess.tsx | Route smoke | Not started
V2-19.02 | Billing And Payments | Stripe session safety | Proof | P1 | Checkout, subscription, SMS credit, and verify session paths remain safe. | Safety tests pass and no key/internal detail is exposed. | stripeService.ts | Stripe safety tests | Not started
V2-19.03 | Billing And Payments | Bypass discipline | Proof | P0 | Testing bypass parameters stay controlled and do not leak into normal product behavior. | Bypass cleanup parity tests pass. | paymentGate.ts | Bypass tests | Not started
V2-19.04 | Billing And Payments | SMS credit readiness | Actual | P2 | SMS credits are clear while live SMS remains compliance-locked. | UI does not imply live SMS sending before approval. | BillingModal.tsx, Messages.tsx | Compliance scan | Not started
V2-19.05 | Billing And Payments | Provider-backed billing proof | Proof | P1 | Stripe checkout, webhook entitlement, recovery, and any SMS-credit billing path have target-environment proof or are explicitly narrowed. | Billing cannot look launch-ready unless checkout, entitlement, recovery, and provider-dependent states are proven or honestly disabled. | PaymentRequired.tsx, stripe functions, billing docs | Stripe live/test proof | In progress | Billing/provider-backed service recovery is safer, but target-environment checkout and entitlement proof are still not closed.
V2-20.01 | Admin, Audit, Errors | Audit log usefulness | Actual | P2 | AuditLogs shows meaningful actor, action, target, and time. | Operators can understand important changes without raw internals. | AuditLogs.tsx | Audit tests | Not started
V2-20.02 | Admin, Audit, Errors | Error log usefulness | Actual | P2 | ErrorLogs groups customer-safe errors with useful recovery context. | No secret/internal values render in error UI. | ErrorLogs.tsx | Error tests | Not started
V2-20.03 | Admin, Audit, Errors | Customer-safe error copy | Proof | P1 | All common failure paths use safe, friendly, actionable copy. | Error helper tests and UI scan pass. | customerSafeError.ts | Safe error tests | Not started
V2-20.04 | Admin, Audit, Errors | Support diagnostics packet | Depth | P2 | Support can collect context without exposing secrets. | Support packet has route, action, time, and safe ids only. | errorLogger.ts | Diagnostics tests | Not started
V2-20.05 | Admin, Audit, Errors | Owner analytics and invite-funnel truth | Depth | P1 | Owner analytics use measured RSVP, registry, photo, invite-open, QR, and guest-input signals without inventing funnel certainty. | Analytics surfaces help owners act while clearly separating measured events from unavailable or partial instrumentation. | Overview.tsx, analyticsAggregate.ts, guest hub event tracking | Analytics truth tests | Not started | Audit-derived V2 readiness gap.
V2-21.01 | AI Layer | Preview before apply | Depth | P1 | AI draft/copy/photo suggestions are previewed before applying. | No AI path mutates user data without visible review. | ai*.ts, Builder | AI tests | Not started
V2-21.02 | AI Layer | User-edit preservation | Proof | P0 | AI never casually overwrites user-edited content. | Preservation tests cover builder, registry, onboarding, and copy patches. | aiBuilderProjectPatch.ts | Preservation tests | Not started
V2-21.03 | AI Layer | Uncertainty model | Depth | P1 | Thin or conflicting input produces clear uncertainty and next question. | AI copy avoids false confidence and routes to confirmation. | aiOnboarding.ts, aiFollowUpPlanner.ts | AI eval tests | Not started
V2-21.04 | AI Layer | Internal detail shielding | Proof | P0 | Provider, key, token, cost, and diagnostic details never appear in user UI. | Leak scan and tests pass. | openai.ts, AI routes | Leak scan | Not started
V2-21.05 | AI Layer | Model-backed lane clarity | Proof | P0 | Every marketed AI lane is explicitly classified as model-backed, deterministic, or intentionally non-AI in product copy and proof. | No customer-facing surface overclaims AI depth or hides whether a result was generated or rule-based. | ai-product-audit docs, onboarding-ai-orchestrate, BuilderV2Lab.tsx | AI readiness proof, copy audit | In progress | Public and owner copy now overclaims less about AI-backed behavior, but the full classified AI product contract is still open.
V2-21.06 | AI Layer | Cross-surface AI contract | Depth | P1 | Onboarding, builder, translation, and photo-intelligence flows share the same review/apply, fallback, and edit-respect contract. | AI feels like one coherent assistant system instead of separate clever pockets. | onboarding-ai-orchestrate, builder-v2, translate-site-content, photo-analyze-batch | Cross-surface AI tests | Not started | Endgame-critical for V2 holy-fuck bar.
V2-21.07 | AI Layer | Grounding and source transparency | Depth | P1 | AI suggestions explain what current project data they used or what is still missing before claiming confidence. | Couples can tell why a suggestion exists and what needs confirmation before trusting it. | aiFollowUpPlanner.ts, setupConcierge.ts, builder AI helpers | AI grounding tests | Not started | Endgame-critical for V2 holy-fuck bar.
V2-21.08 | AI Layer | End-to-end AI outcome proof | Proof | P0 | Browser/mobile proof covers real couple flows through Quick Start, builder suggestions, translation, and photo intelligence on the shipped runtime. | The AI system can be marketed without hand-wavy caveats about whether it really works end to end. | proof:v1 ai lanes, builder/runtime proof | Live AI browser proof | Not started | Endgame-critical for V2 holy-fuck bar.
V2-22.01 | Data Integrity | Canonical adapter sweep | Proof | P0 | Canonical page/section adapters have one source of truth. | Adapter tests cover V1/V2/public/import paths. | canonical*.ts | Adapter tests | Not started
V2-22.02 | Data Integrity | Hydration normalization | Proof | P0 | Loaded storage data normalizes before UI consumes it. | Malformed persisted state is repaired or clearly rejected. | storage/hydration helpers | Hydration tests | Not started
V2-22.03 | Data Integrity | Import/export versioning | Actual | P0 | Every import/export records schema version and repair report. | Unknown versions get safe error or migration path. | builder-v2/import*.ts | Import/export tests | Not started
V2-22.04 | Data Integrity | Product integrity reports | Actual | P1 | Registry, builder, RSVP, guest, and planning integrity reports are visible to operators. | Reports separate fixed, risky, and deferred issues. | registryTruthSweepReport.ts | Integrity tests | Not started
V2-23.01 | Security And Privacy | Token flow audit | Proof | P0 | RSVP, guest, vault, invite, and upload tokens are validated and never leaked. | Token safety tests and route scan pass. | token helpers | Safety tests | Not started
V2-23.02 | Security And Privacy | Service-role authorization | Proof | P0 | Service-role paths are authorized and proofed without exposing secrets. | proof:v1 service-role authorization passes when env is available. | Supabase funcs | Proof command | Not started
V2-23.03 | Security And Privacy | Upload and URL safety | Proof | P0 | Uploads and external URLs are sanitized and constrained. | Unsafe URLs and upload misuse are rejected safely. | urlUtils.ts, photo upload | Safety tests | Not started
V2-23.04 | Security And Privacy | Docs/log secret scan | Proof | P0 | Docs, logs, UI, and screenshots do not expose keys/internal diagnostics. | Secret scan has no actionable findings. | docs, src | Secret scan | Not started
V2-24.01 | Accessibility, Mobile, Performance | Mobile route matrix | Proof | P1 | Major public, guest, dashboard, coordinator, and builder routes render on mobile. | No core task blocked by overlap or desktop-only controls. | All major routes | Browser smoke | Not started
V2-24.02 | Accessibility, Mobile, Performance | Keyboard and form accessibility | Proof | P1 | Core forms and dashboards are keyboard navigable with sane labels. | No critical unlabeled controls in main flows. | Forms/components | A11y spot checks | Not started
V2-24.03 | Accessibility, Mobile, Performance | Performance budget | Proof | P2 | Public and builder pages stay within reasonable load/render budgets. | Build chunks and public route loads do not regress materially. | Build output, routes | Build/perf scan | Not started
V2-24.04 | Accessibility, Mobile, Performance | Layout overlap audit | Proof | P1 | No major card/button/text overlap in high-traffic surfaces. | Desktop and mobile screenshots pass visual review. | Major UI routes | Screenshot proof | Not started
V2-24.05 | Accessibility, Mobile, Performance | Whole-product visual polish matrix | Proof | P1 | Representative guest, owner, builder, coordinator, and memory flows get desktop/mobile visual review for overlap, density, dead ends, and first-impression quality. | The product feels polished across the paths a real couple or guest will touch first, not only in isolated tested components. | Core routes, Playwright/browser proof, screenshots | Visual matrix proof | Not started | Audit-derived V2 readiness gap.
V2-25.01 | Proof, QA, Release | V2 proof board | Actual | P0 | Proof board gets V2 milestone status and latest verified commit. | Board reflects branch truth and does not lag production/local reality. | docs/v1-smoke-proof-log.md | proof board command | Not started
V2-25.02 | Proof, QA, Release | Feature proof scripts | Actual | P0 | Major V2 feature lanes have focused proof commands. | Each P0/P1 lane can be verified without running everything manually. | package scripts, proof scripts | Proof commands | Not started
V2-25.03 | Proof, QA, Release | Milestone QA cadence | Proof | P0 | Mega batches use focused checks per batch and full audits at milestone boundaries. | Tracker status and branch status stay honest. | docs, tracker | QA audit | Not started
V2-25.04 | Proof, QA, Release | Release and rollback plan | Proof | P0 | V2 release has notes, known waivers, rollback path, and deploy decision record. | Release packet exists before production deploy. | docs | Release review | Not started
V2-25.05 | Proof, QA, Release | Tracker and proof reconciliation | Proof | P0 | The V2 tracker, proof board, shipped commits, and release notes agree on what is done, partial, blocked, and intentionally deferred. | No overnight batch works from stale milestone status or claims completion without matching proof. | dayof-full-v2-milestone-tracker.xlsx, proof board scripts, release notes | Tracker/proof audit | In progress | Tracker rows now reflect Builder V2 cutover, public truth, RSVP/registry progress, and customer-safe hardening more honestly; continue row-by-row reconciliation.
V2-25.06 | Proof, QA, Release | Consumer-ready V2 certification | Proof | P0 | V2 is not called done until all P0/P1 consumer-facing flows are proven, polished, truthful, mobile-safe, and free of blocking release risk. | The release owner can walk a real couple and guest through the product without caveats beyond explicitly narrowed, non-marketed deferrals. | V2 Exit Bar, Feature Audit, proof board, release notes, core routes | Full exit-bar readback, visual proof matrix, focused suites, typecheck, lint, build/full tests at release boundary | In progress | Certification remains explicitly blocked until all V2 exit-bar gates are green or honestly narrowed; current blockers still include G02/G03/G04/G05/G06/G07/G08 proof gaps.

## QA Gates
Gate Level | Gate | Requirement | How We Use It
Micro milestone | Focused tests for touched modules | Required | Run every micro milestone when behavior changes.
Micro milestone | Touched-file eslint | Required | Avoid adding new lint while repo-wide lint debt exists.
Micro milestone | Typecheck | Conditional | Run when shared types/contracts/components changed.
Micro milestone | git diff --check | Required | Run before any commit.
Batch milestone | npm run build | Required | Run at batch boundary or when bundling/runtime may change.
Batch milestone | Full npm test | Required | Run at milestone boundary, before deploy, or after cross-system changes.
Batch milestone | Browser smoke | Required for UI | Use local browser proof for changed high-traffic routes when available.
Release milestone | Proof board refresh | Required | Proof docs must reflect the release candidate commit.
Release milestone | Known waiver list | Required | Any lint/env/browser limitations must be explicit.
Release milestone | Rollback plan | Required | Production deploy needs rollback or V1 fallback story.
V2 release exit | All P0/P1 consumer blockers closed | Required | V2 cannot be called done while any P0/P1 consumer-facing milestone, audit row, or exit-bar gate remains open without an explicit narrowed claim.
V2 release exit | Consumer-ready walkthrough | Required | Run a real couple + guest walkthrough across onboarding, builder, public site, RSVP, travel, messaging state, registry, photos, and vault before V2 signoff.
V2 release exit | No overclaim copy gate | Required | Claims matrix, feature audit, and public/guest copy must agree with shipped behavior; deferred provider/API features must not be marketed as live.
V2 release exit | Mobile visual proof matrix | Required | Core owner and guest routes need desktop/mobile screenshot proof with no major overlap, dead ends, or unusable controls.
V2 release exit | Provider-gated feature proof or narrowing | Required | SMS, billing, AI model-backed lanes, vault provider depth, and analytics must be either live-proven or explicitly narrowed in UI/docs.
V2 release exit | Full release verification bundle | Required | At the release boundary run focused suites, touched-file eslint, typecheck, git diff --check, build, and full/high-risk tests; document any waiver.

## Batch Plan
Batch | Name | Milestones | Purpose | Priority | Exit Signal | Closeout bucket | Current evidence state | Immediate next action | Exit-bar gate(s)
Batch 1 | Builder V2 release spine | V2-03, V2-04, V2-05, V2-22 | Make V2 real: schema, multi-page, runtime, migration, data integrity. | P0 | V2 doc renders publicly and can migrate from existing truth. | Actual work + test-first | Builder automated gate green; public runtime/template parity not green. | Run builder browser smoke, then public runtime/template parity work. | V2-G03, V2-G04
Batch 2 | Guest and RSVP spine | V2-06, V2-07, V2-09 | Unify guest journey, RSVP, event RSVP, contact updates, guest ops. | P1 | Guest can move end-to-end without stale tokens or ops leaks. | Test-first | Pieces are safer; unified guest proof still open. | Run invite-linked mobile guest happy-path and stale-link recovery proof. | V2-G05
Batch 3 | Registry operating system | V2-08 | Owner registry, public registry, imports, cleanup, funds, thank-yous. | P1 | Registry public and dashboard truth stays synchronized. | Test-first | Registry owner polish advanced; public parity proof open. | Run public registry parity proof and focused registry suite. | V2-G09
Batch 4 | Messaging, texting, and day-of command | V2-10, V2-14 | Preview-safe messaging, texting readiness, delivery recovery, and coordinator command center. | P0 | Day-of operator can resolve issues and the SMS lane is ready for explicit enablement. | Provider-gated/narrow | Messaging copy safer; SMS provider/compliance/live proof not green. | Keep SMS narrowed/disabled or prove sender, consent, opt-out, live delivery, and credits. | V2-G06
Batch 5 | Planning, itinerary, seating | V2-11, V2-12, V2-13 | Make planning data operational across vendors, timing, travel, seating. | P1 | Planning recommendations route to real actions and handoffs. | Work/proof | Planning/travel/seating remain broad P1 depth lanes. | Work after P0 exit-bar blockers unless a gate failure points here. | V2-G05, V2-G13
Batch 6 | Memory delight and post-wedding | V2-15, V2-16 | Photos, vault, upload delight, curation, keepsake, and name-change assistant. | P2 | Memory capture feels premium, safe, and recoverable. | Work + proof | Photo/vault/memory delight gate not started. | Run mobile upload/vault/recap proof and patch rough edges. | V2-G08
Batch 7 | Settings and collaboration trust | V2-17, V2-18 | Role enforcement, invites, site access, identity export, site switching. | P1 | Permissions and settings are understandable and enforced. | Proof-first | Permissions/settings need focused access proof. | Run collaborator/access/site-switching proof in security closeout. | V2-G12
Batch 8 | Billing, admin, security | V2-19, V2-20, V2-23 | Payment safety, admin logs, error safety, privacy/security audit. | P0 | No secret leaks; billing and ops states are safe. | Proof/narrow | Billing/security/admin are release-sensitive. | Run bypass/Stripe/security/safe-error proofs; narrow unsupported claims. | V2-G10, V2-G11, V2-G12
Batch 9 | AI trust and product depth | V2-21 | Preview-before-apply, edit preservation, uncertainty, grounding, end-to-end proof, and internal shielding. | P1 | AI feels cohesive, honest, and safe to market. | Proof infra + narrowing | AI readiness proof command is stale/missing. | Restore AI readiness proof and classify AI claims. | V2-G07, V2-G01
Batch 10 | Experience and release proof | V2-24, V2-25 | Mobile, accessibility, performance, proof board, release packet. | P0 | Release candidate has honest proof and rollback plan. | Release proof | Proof board freshness stale; final visual/release docs open. | Repair proof infrastructure, run visual matrix, reconcile tracker/proof docs, write rollback plan. | V2-G13, V2-G14

## Legend
Label | Meaning
Status | Meaning
Not started | No implementation work has begun in this tracker.
Scoping | Files and exact task shape are being inspected.
In progress | Implementation is active.
Blocked | Needs credential, product decision, environment, or upstream unblock.
Needs proof | Implementation appears done but verification is incomplete.
Done | Exit criteria and proof requirements are satisfied.
Gap type: Actual | Missing capability or incomplete product path.
Gap type: Depth | Works, but not yet full V2 product quality.
Gap type: Proof | Likely okay or partially okay, but needs verification/release confidence.
Gap type: Hygiene | Maintainability, lint, docs, or operational cleanup.

## Audit Log
Timestamp PT | Audit Area | Finding | Evidence | Next Action
2026-05-28 04:51 PM PT | V2 Exit Bar | V2 is not signoff-ready yet. | Tracker audit: V2 Exit Bar has 0/14 Done; 8 In progress; 6 Not started. | Close or explicitly narrow every V2-G gate before calling V2 complete.
2026-05-28 04:51 PM PT | Builder V2 proof | Builder V2 automated gate is now green after typecheck fixture repairs. | npm run proof:v1:builder-v2-ci-gate passed: typecheck, 50 Builder V2 tests, 9 cutover proof checks, and build. | Still perform signed-in owner browser smoke for /dashboard/builder, /dashboard/builder-guide, and legacy fallback feel.
2026-05-28 04:51 PM PT | Release proof drift | Launch/proof gate wiring is not trustworthy until stale/missing script references are reconciled. | Inventory found many package.json proof scripts pointing at absent scripts; npm run proof:v1:ai-product-readiness fails before testing behavior. | Decide whether to restore proof scripts, replace stale scripts, or remove/narrow obsolete gates with honest claims.
2026-05-28 04:51 PM PT | Proof board freshness | Canonical proof-board freshness is stale. | npm run proof:v1:board:freshness fails because BACKLOG.md current-state metadata is stale. | Refresh BACKLOG.md current-state truth or stop using proof:v1:board as current release truth.
2026-05-28 04:51 PM PT | V2 remaining work | Large P0/P1 product work remains beyond tests. | Tracker audit: Master Milestones have 0 Done, 8 In progress, 17 Not started; Micro Milestones have 2 Done, 16 In progress, 105 Not started. | Separate test-only closures from actual unbuilt/narrowed V2 gates and work the exit bar first.
2026-05-28 04:57 PM PT | Milestone queue update | Added operational closeout queue and testing/build split without marking unfinished gates done. | New sheets: V2 Closeout Queue and Testing vs Build Split. V2 Exit Bar now includes closeout buckets and latest evidence columns. | Use V2 Closeout Queue rank order for the next implementation/proof batches; update gates only when evidence is green or claims are narrowed.
2026-05-28 05:51 PM PT | AI proof restoration | Restored ai-product-readiness proof and removed browser-side Vite OpenAI key path. | npm run proof:v1:ai-product-readiness passed 7/7; src/lib/openai.ts now reads OPENAI_API_KEY / OPENAI_MODEL only, so Quick Start and draft generation prove deterministic fallback instead of browser-key AI. | Keep V2-G07 In progress until cross-surface claims review and any retained server-backed AI lanes are fully reconciled.
2026-05-28 05:54 PM PT | Proof board freshness | Refreshed BACKLOG current-state truth so the proof board is fresh again. | `npm run proof:v1:board:freshness` passed and `npm run proof:v1:board:md` rendered cleanly after updating the BACKLOG current-state block without changing deployed launch claims. | Keep V2-G14 In progress until the broader release-proof contract and any remaining stale proof references are reconciled.